## Sheet1
vendor | project | activity | start | end | %complete
M/s Binod Enterprises | Construction of New Ethanol Tank | Site Mobilisation | 2025-11-06 | 2025-11-20 | 100
|  | Desgin & Drawing | 2025-11-13 | 2025-12-04 | 80
|  | Fire screen around Tank | 2025-11-21 | 2025-12-04 | 0
|  | Bottom & Annular Fabrication & Erection | 2026-01-15 | 2026-02-05 | 20
|  | Shell Fabrication & Erection | 2026-02-06 | 2026-06-26 | 50
|  | Floating Deck Fabrication & Erection | 2026-02-06 | 2026-03-13 | 30
|  | Roof Structure Fabrication & Erection | 2026-02-13 | 2026-03-13 | 20
|  | Roof Plate Fabrication & Erection | 2026-03-14 | 2026-04-25 | 50
|  | Internal Painting | 2026-06-27 | 2026-07-25 | 10
|  | External Painting & Logo | 2026-07-26 | 2026-08-09 | 0
|  | Primary & Secondary Seal Erection | 2026-04-26 | 2026-05-17 | 0
|  | Hydrotest | 2026-06-21 | 2026-07-12 | 0
|  | Pivot Master Supply & Erection | 2026-07-26 | 2026-08-09 | 0
|  | Sprinkler System erection | 2026-05-24 | 2026-06-14 | 0
|  | Handover | 2026-08-02 | 2026-08-16 | 0
M/s Binod Enterprises | Tank 5B Works
|  | API Inspector Audit | 2025-11-06 | 2025-11-13 | 100
|  | Desgin & Drawing | 2025-11-14 | 2025-12-05 | 80
|  | Fire screen around Tank | 2025-11-14 | 2025-11-28 | 100
|  | Floating deck dismantling | 2025-11-29 | 2026-01-03 | 100
|  | Floating deck fabrication & erection | 2025-12-06 | 2026-02-28 | 50
|  | Internal Painting | 2026-03-01 | 2026-03-29 | 0
|  | External Painting & Logo | 2026-05-17 | 2026-06-07 | 0
|  | Primary & Secondary Seal Erection | 2026-03-21 | 2026-04-04 | 0
|  | Hydrotest | 2026-04-05 | 2026-04-26 | 0
|  | Stair Dismantling | 2026-06-21 | 2026-06-28 | 0
|  | Stair Fabrication & erection | 2026-06-29 | 2026-07-13 | 0
|  | Roof Structure Fabrication & Erection | 2026-06-29 | 2026-08-03 | 0
|  | Roof Plate Fabrication & Erection | 2026-07-21 | 2026-08-25 | 0
|  | Pivot Master Erection | 2026-08-26 | 2026-09-02 | 0
|  | Handover | 2026-09-03 | 2026-09-17 | 0
M/s Binod Enterprises | Tank 5A Works
|  | API Inspector Audit | 2026-09-18 | 2026-09-25 | 0
|  | Desgin & Drawing | 2026-09-26 | 2026-10-17 | 0
|  | Fire screen around Tank | 2026-09-26 | 2026-10-10 | 0
|  | Floating deck dismantling | 2026-10-11 | 2026-11-15 | 0
|  | Floating deck fabrication & erection | 2026-10-18 | 2027-01-10 | 0
|  | Internal Painting | 2027-01-11 | 2027-02-08 | 0
|  | External Painting & Logo | 2027-03-29 | 2027-04-19 | 0
|  | Primary & Secondary Seal Erection | 2027-01-02 | 2027-01-16 | 0
|  | Hydrotest | 2027-01-17 | 2027-02-07 | 0
|  | Stair Dismantling | 2027-04-05 | 2027-04-12 | 0
|  | Stair Fabrication & erection | 2027-04-13 | 2027-04-27 | 0
|  | Roof Structure Fabrication & Erection | 2027-04-13 | 2027-05-18 | 0
|  | Roof Plate Fabrication & Erection | 2027-05-04 | 2027-06-08 | 0
|  | Pivot Master Erection | 2027-06-09 | 2027-06-16 | 0
|  | Handover | 2027-06-17 | 2027-07-01 | 0
M/s K Kumarraja Projects Pvt Ltd | Construction of New control room building at Visakha Installation | Mobilisation | 2025-07-21 | 2025-08-03 | 100
|  | Earth Work | 2025-08-04 | 2025-08-20 | 100
|  | Pile Foundation | 2025-08-21 | 2025-09-10 | 100
|  | Control Room Construction | 2025-09-20 | 2025-12-04 | 90
|  | Finishing Work | 2025-12-05 | 2026-01-03 | 10
|  | Electrical & Other Works | 2025-11-04 | 2026-01-03 | 0
|  | Handing Over | 2026-01-04 | 2026-01-20 | 0
M/s Times Projects | Roof replacement work in EFR Tank No. 4B (dia 23 m × height 14 m) at Vizag Installation | Dismantling | 2025-06-10 | 2025-06-27 | 100
|  | Drawing & Design | 2025-05-28 | 2025-06-10 | 100
|  | Shell Plate Weld | 2025-06-17 | 2025-07-18 | 10
|  | Roof Plate Weld | 2025-06-27 | 2025-10-27 | 90
|  | Roof Appurtenances | 2025-10-18 | 2025-11-27 | 0
|  | Rim Seal System | 2025-07-27 | 2025-11-27 | 0
|  | Painting | 2025-11-17 | 2025-12-18 | 0
|  | Hand Over | 2025-12-18 | 2025-12-27 | 0
M/s Sai Sri Constructions | Pile Foundation works for New Ethanol Tank at Visakha POL Installation | Mobilisation | 2025-08-26 | 2025-09-08 | 100
|  | Fire Screen | 2025-09-02 | 2025-09-25 | 100
|  | Clearance & Survey | 2025-09-02 | 2025-09-15 | 100
|  | Piling 550mm | 2025-09-02 | 2025-11-08 | 100
|  | Initial Load Tests | 2025-10-16 | 2025-12-16 | 100
|  | Lateral Load Tests | 2025-10-16 | 2025-12-16 | 100
|  | Routine Load Tests | 2025-10-16 | 2025-12-09 | 100
|  | Routine Pullout Tests | 2025-11-01 | 2025-12-16 | 100
|  | Excavation | 2025-10-02 | 2025-12-02 | 100
|  | Chipping | 2025-10-02 | 2025-12-02 | 100
|  | Pile Integrity Tests | 2025-10-09 | 2025-12-09 | 100
|  | PCC & RCC (Cap & SS) | 2025-10-09 | 2025-12-16 | 100
|  | Structural Steel | 2025-10-09 | 2025-12-16 | 100
|  | Sand Filling | 2025-10-16 | 2025-12-25 | 100
|  | Bitumen Carpet (50mm) | 2025-11-01 | 2025-12-25 | 95